## Risk Register
Risk ID | Risk Name | Risk Category | Risk Description | Risk Owner | Existing Control | Recommended Control | Likelihood | Impact | Current Risk Level | Target Risk Level
R-001 | Inactive User Access | Access Control / Identity Management | Inactive user accounts retain access to critical systems, increasing risk of unauthorized access | IT Team + HR | Manual deactivation process | Automated de-provisioning, HR-IAM integration, periodic reviews | High | High | High | Medium
R-002 | Excess Privileged Access | Privileged Access Management | Users have administrative privileges beyond requirement | IT Team | Partial RBAC | Enforce least privilege, PAM, approval workflows | Medium | High | High | Medium
R-003 | Unauthorized DB Access | Data Security / Privacy | Unauthorized roles have access to customer database | IT + Data Owner | Limited restrictions | Strict RBAC, data masking, access approvals | Medium | High | High | Medium
R-004 | RBAC Violations | Access Control | Access levels inconsistent with roles | IT Team | Basic role mapping | Strengthen RBAC, periodic validation | High | Medium | High | Low
R-005 | Weak User Lifecycle | Identity Management | Ineffective onboarding/offboarding leading to excess access | HR + IT | Manual processes | Automate lifecycle, integrate HR & IAM | High | High | High | Medium
R-006 | No Periodic Access Review | Governance / Compliance | Lack of periodic access review causing accumulation of excess access | IT + Compliance | Ad-hoc reviews | Quarterly access reviews, automated workflows | High | Medium | High | Low