## Action Plan
Risk ID | Risk Name | Action | Owner | Priority | Timeline
R-001 | Inactive User Access | Disable all inactive user accounts immediately | IT Team | High | 1 week
R-001 | Inactive User Access | Implement automated de-provisioning integrated with HR system | IT Team + HR | High | 1-2 months
R-002 | Excess Privileged Access | Review all admin accounts and remove unnecessary privileges | IT Team | High | 2 weeks
R-002 | Excess Privileged Access | Implement Privileged Access Management (PAM) | IT Team | Medium | 2-3 months
R-003 | Unauthorized DB Access | Remove database access for unauthorized roles | IT Team | High | 1-2 weeks
R-003 | Unauthorized DB Access | Implement data masking for sensitive data | IT Team | Medium | 1-2 months
R-004 | RBAC Violations | Review and correct user access based on roles | IT Team | High | 2 weeks
R-004 | RBAC Violations | Update and standardize RBAC policies | IT Team | Medium | 1 month
R-005 | Weak User Lifecycle | Integrate HR system with IAM for lifecycle management | IT + HR | High | 2 months
R-006 | No Periodic Access Review | Implement quarterly access review process | IT + Compliance | High | 1 month