## Sheet2
Risk ID | Risk Level | Risk Owner | Existing Controls | Recommended Controls | Risk Treatment | Target Risk Level
R1 | High | Application Developer | Basic authentication mechanism | Input validation, parameterized queries, Web Application Firewall (WAF) | Mitigate | Medium
R2 | High | Backend Developer | Basic API authentication | Input validation, secure API design, parameterized queries, API security testing | Mitigate | Medium
R3 | High | IT Administrator | Basic firewall protection | Advanced firewall configuration, DDoS protection, rate limiting | Mitigate | Medium
R4 | High | IT Administrator | Username-password based authentication without MFA | Multi-Factor Authentication (MFA), strong authentication policies | Mitigate | Medium
R5 | Medium | Finance Manager | Basic access permissions | Role-Based Access Control (RBAC), access reviews | Mitigate | Low
R6 | High | IT Administrator + Operations Manager | Third-party payment gateway with basic security controls | TLS encryption, vendor security assessment, secure API communication | Mitigate | Medium
R7 | Medium | IT Administrator | Antivirus software | Centralized logging, SIEM implementation, endpoint monitoring | Mitigate | Low
R8 | High | Application Developer | Absence of SSL/TLS encryption for web communication | SSL/TLS implementation, secure communication protocols | Mitigate | Medium
R9 | Medium | Operations Manager | Informal vendor agreements | Vendor security policies, contractual controls, periodic audits | Mitigate | Low
R10 | Low | Operations Manager | Basic infrastructure setup | Data backup, disaster recovery plan, offsite storage | Mitigate | Low