## Sheet4
Risk ID | Risk Scenario | Risk Level | Treatment Action | Implementation Steps | Priority | Risk Owner | Status
R1 | SQL Injection on E-Commerce Web Application | High | Mitigate | Implement input validation, use parameterized queries, deploy WAF | High | Application Developer | Open
R2 | SQL Injection on Backend/API | High | Mitigate | Implement secure API design, input validation, parameterized queries, and conduct API security testing | High | Backend Developer | Open
R3 | DDoS Attack on Network Devices | High | Mitigate | Configure advanced firewall rules, implement DDoS protection and rate limiting, and enable network monitoring | High | IT Administrator | Open
R4 | Broken Authentication – Customer Data | High | Mitigate | Implement Multi-Factor Authentication (MFA), enforce strong password policies, and strengthen authentication mechanisms | High | IT Administrator | Open
R5 | Insider Misuse – Financial Data | Medium | Mitigate | Implement Role-Based Access Control (RBAC), enforce least privilege, and conduct periodic access reviews | Medium | Finance Manager | Open
R6 | Payment Data Exposure (Third-Party) | High | Mitigate | Implement TLS encryption, validate third-party security controls, and ensure secure API communication with vendors | High | IT Administrator + Operations Manager | Open
R7 | Malware / Insider Misuse (Workstations) | Medium | Mitigate | Implement centralized logging, deploy SIEM monitoring, and strengthen endpoint security controls | Medium | IT Administrator | Open
R8 | Man-in-the-Middle Attack | High | Mitigate | Implement SSL/TLS encryption, enforce secure communication protocols, and validate certificate configurations | High | Application Developer | Open
R9 | Third-Party Data Breach | Medium | Mitigate | Establish vendor security policies, include security clauses in contracts, and perform periodic vendor risk assessments | Medium | Operations Manager | Open
R10 | Natural Disaster – Server Loss | Low | Mitigate | Implement regular data backups, establish disaster recovery plan, and maintain offsite backup storage | Low | Operations Manager | Open